## Project Planner
Project Plan
# | ACTIVITY | PLAN START | PLAN END DATE | DEPENDEN-CIES | PERCENT COMPLETE
Project Requirements:
1 | Define the Problem / Project focus / Story we want to tell | 2020-10-31 | 2020-11-03 |  | 100% | Find a problem worth solving, analyzing or vlsualizing.
2 | Determine the type of project | 2020-10-31 | 2020-11-03 | 1 | 100% | Use ML in the context of technologies learned.
3 | Find the DataSets to use in the project; determine which timeframe we want for our data | 2020-10-31 | 2020-11-03 | 1 | 100% | You must use:Scikit-Learn and/or another machine learning library.
4 | Determine if we will be using Python, Python Matplotlib, HTML / CSS / Bootstrap, JavaScript Plotly, JavaScript D3.js, JavaScript leaflet, SQL Database, MongoDB, Google Cloud SQL, Amazon AWS, Tableau | 2020-10-31 | 2020-11-03 | 1 | 100% | You must use at least two of the tools learned in this course.
5 | Determine which host application we will be using; Heroku or other (Heroku) | 2020-10-31 | 2020-11-03 | 1 | 100% | Host application using Heroku or tool of your choice.
6 | Determine project schedule / meeting dates & times | 2020-10-31 | 2020-11-03 | 1 | 0%
7 | Write and submit the proposal | 2020-10-31 | 2020-11-03 | 1 | 100%
8 | Create repo on GitHub | 2020-11-03 | 2020-11-03 | 1 | 100%
9 | Determine dependencies for hosting application |  |  | 8 | 0%
10 | Add project steps for chosen hosting option |  |  | 9 | 0%
11 | Load the Data; import needed libraries |  |  | 10 | 0%
12 | Determine the shape (dimensions) of the data |  |  | 11 | 0%
13 | Explore the data (review it) |  |  | 12 | 0%
14 | Clean the data; join datasets, dropping or completing missing data, dropping unnecessary data, update data types, etc |  |  | 13 | 0%
15 | Define uncommon terms or abbreviations used in data |  |  | 13 | 0%
16 | Determine the statistical analyses to be included |  |  | 14
17 | Perform any necessary statistical analyses |  |  | 14 | 0%
18 | Design template for app; including projected visualizations |  |  | 14 | 0%
19 | Create connections to postgres |  |  | 17 | 0%
20 | Save the schemas in SQL for flask app |  |  | 19 | 0%
21 | Create the flask app |  |  | 20 | 0%
22 | Create index.html template |  |  | 21 | 0%
23 | Create the Heroku app routes |  |  | 22 | 0%
24 | Deploy index.html template to heroku |  |  | 23 | 0%
25 | Explore the data with visualizations; box plots, scatterplots, bar charts, etc. |  |  | 18 | 0%
26 | Create a validation dataset |  |  | 17 | 0%
27 | Split the data into training and testing data |  |  | 26 | 0%
28 | Build models; test the algorithms to determine which would be best to use |  |  | 27 | 0%
29 | Fit the model to the training data |  |  | 28 | 0%
30 | Make predictions |  |  | 29 | 0%
31 | Evaluate Predictions |  |  | 30 | 0%
32 | Deploy host application |  |  | 31 | 0%
33 | Prepare a 15-minute data deep-dive or infrastructure walkthrough that shows machine learning in the context of what we've already learned. |  | 2020-11-12 | 32 | 0%
34 | Practice Presentation |  | 2020-11-12 | 33 | 0%